## MASTER
Place an "x" in all boxes that apply
Ex: | Full | Often | Sometimes | Intermittent
|  |  | X | X
Planning |  |  |  |  | Execution
1 | Level of customer participation on the project team |  |  |  | 6 | Level of team oversight needed
| Full | Often | Sometimes | Intermittent |  | High | Medium | Low
| SCRUM | Kanban | DMAIC | Waterfall |  | Waterfall | Kanban | SCRUM
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
2 | Level of requirement/user story details needed prior to the start of execution |  |  |  | 7 | Ability to respond to changes to scope, timeline, and/or resources
| High | Medium High | Medium | Low |  | Easy | Moderate | Difficult
| Waterfall | DMAIC | SCRUM | Kanban |  | Kanban | SCRUM | Waterfall
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
3 | Project team methodology preference/ experience |  |  |  | 8 | Level of dependencies within the project
| Waterfall | DMAIC | SCRUM | Kanban |  | Many | Some | Few
| Waterfall | DMAIC | SCRUM | Kanban |  | Waterfall | SCRUM | Kanban
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
4 | Primary project driver |  |  |  | 9 | Level of vendor management
| Process | Timeline | Unfamiliar | Functionality |  | High | Medium | Low or N/A
| DMAIC | Waterfall | Kanban | SCRUM |  | Waterfall | SCRUM | Kanban
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
5 | Ongoing measures required post project |  |  |  | 10 | Delivery approach
| Required | Recommended | Optional | Rarely/ N/A |  | Iterative | Constant Flow | Big Bang
| DMAIC | Waterfall | SCRUM | Kanban |  | SCRUM | Kanban | Waterfall
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| Planning Methodology |  |  |  |  | Execution Methodology
| DMAIC | Waterfall | SCRUM | Kanban |  | Waterfall | SCRUM | Kanban
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
| 0 | 0 | 0 | 0 |  | 0 | 0 | 0
Combine highest method(s)

## Instructions
EPMO Methodology Selection Tool
Instructions
1 | Make a Copy ¦ Download as Excel |  | EPMO Methodology Selection Tool
2 | Answer each question for the project, more than 1 answer is perfectly acceptable
3 | Identify top scoring methodologies for Planning and Execution
4 | Combine Planning and Execution to identify best pure or blend options. See sample1 and sample2
5 | If a blend, use the Blend Matrix to guide decision on which to choose |  | Agile Methodology Blends Matrix
To Modify/Change Methodology Options
1 | If project factors change, repeat steps above to adjust the methodology
Tool Reference (original tool courtesy of University of Notre Dame PMO)
ntrda.me/decision
ntrda.me/blends
EPMO References
EPMO Agile Reference Manual
Definitions (also refer to PMI Agile Practice Guide)
| Lean | A set of principles that have been taken from lean manufacturing approaches and applied to software development. Resource: www.sixsigmacouncil.org
| DMAIC | An acronym for Define, Measure, Analyze, Improve and Control; refers to a data-driven improvement cycle used for improving, optimizing and stabilizing business processes and designs; core tool used to drive Six Sigma projects. Resource: www.sixsigmacouncil.org
| Scrum | A single-team process framework for product development and other knowledge work; it includes Scrum roles, events, artifacts, and rules with an iterative approach and time boxed sprints. Resource: www.scrumguides.org
| Waterfall | The waterfall model is a sequential design process for software development processes, in which progress is seen as flowing steadily downwards (like a waterfall) through the phases of conception, initiation, analysis, design, construction, testing, production/implementation and maintenance.
| Kanban | A means to design, manage, and improve flow systems for knowledge work; it includes visualizing an organization’s existing workflow using a Kanban Board, limiting work in progress (WIP) and to stop starting and start finishing work. Resource: Anderson, David J. (April 2010). Kanban: Successful Evolutionary Change for Your Technology Business
| eXtreme Programming (XP) | Aims to produce higher quality software, and higher quality of life for the development team; XP is the most specific of the agile frameworks regarding appropriate engineering practices for software development. Resource: www.extremeprogramming.org
| Crystal Methods | A family of methodologies designed to scale methods to fit the project.
| Feature-Driven Development | An iterative and incremental software development process; it is lightweight and blends several industry-recognized best practices into a cohesive whole. Its main purpose is to deliver tangible, working software repeatedly in a timely manner.
| Dynamic Systems Development Method (DSDM) | One of the earlier agile methods, and it started out prescriptive and detailed. Its coverage of the project life cycle is broad, encompassing aspects of an agile project ranging from feasibility to implementation.

## sample1
Place an "x" in all boxes that apply | [6 empty] | Combine highest method(s)
Ex: | Full | Often | Sometimes | Intermittent
|  |  | X | X
Planning | [5 empty] | Execution
1 | Level of customer participation on the project team |  |  |  |  | 6 | Level of team oversight needed
| Full | Often | Sometimes | Intermittent |  |  | High | Medium | Low
|  | x | x |  |  |  |  | x
| SCRUM | Kanban | DMAIC | Waterfall |  |  | Waterfall | Kanban | SCRUM
| 0 | 1 | 1 | 0 |  |  | 0 | 1 | 0
2 | Level of requirement/user story details needed prior to the start of execution |  |  |  |  | 7 | Ability to respond to changes to scope, timeline, and/or resources
| High | Medium High | Medium | Low |  |  | Easy | Moderate | Difficult
|  | x | [5 empty] | x
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Kanban | SCRUM | Waterfall
| 0 | 1 | 0 | 0 |  |  | 0 | 1 | 0
3 | Project team methodology preference/ experience |  |  |  |  | 8 | Level of dependencies within the project
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Many | Some | Few
| x |  | x | x |  |  |  | x
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Waterfall | SCRUM | Kanban
| 1 | 0 | 1 | 1 |  |  | 0 | 1 | 0
4 | Primary project driver |  |  |  |  | 9 | Level of 3rd party vendor management (e.g. RFP)
| Process | Timeline | Unfamiliar | Functionality |  |  | High | Medium | Low or N/A
|  |  | x | x |  |  |  | x
| DMAIC | Waterfall | Kanban | SCRUM |  |  | Waterfall | SCRUM | Kanban
| 0 | 0 | 1 | 1 |  |  | 0 | 1 | 0
5 | Ongoing measures required post project |  |  |  |  | 10 | Delivery approach
| Required | Recommended | Optional | Rarely/ N/A |  |  | Iterative | Constant Flow | Big Bang
|  |  |  | x |  |  | x | x
| DMAIC | Waterfall | SCRUM | Kanban |  |  | SCRUM | Kanban | Waterfall
| 0 | 0 | 0 | 1 |  |  | 1 | 1 | 0
| Planning Methodology | [5 empty] | Execution Methodology
| DMAIC | Waterfall | SCRUM | Kanban |  |  | Waterfall | SCRUM | Kanban
| 1 | 0 | 0 | 1 |  |  | 0 | 0 | 1
| 1 | 0 | 0 | 0 |  |  | 0 | 1 | 0
| 0 | 1 | 1 | 1 |  |  | 0 | 1 | 0
| 0 | 0 | 1 | 1 |  |  | 0 | 1 | 0
| 0 | 0 | 0 | 1 |  |  | 0 | 1 | 1
| 2 | 1 | 2 | 4 |  |  | 0 | 4 | 2
Kan-SCRUM

## sample2
Place an "x" in all boxes that apply | [6 empty] | Combine highest method(s)
Ex: | Full | Often | Sometimes | Intermittent
|  |  | X | X
Planning | [5 empty] | Execution
1 | Level of customer participation on the project team |  |  |  |  | 6 | Level of team oversight needed
| Full | Often | Sometimes | Intermittent |  |  | High | Medium | Low
|  | x | x |  |  |  |  | x
| SCRUM | Kanban | DMAIC | Waterfall |  |  | Waterfall | Kanban | SCRUM
| 0 | 1 | 1 | 0 |  |  | 0 | 1 | 0
2 | Level of requirement/user story details needed prior to the start of execution |  |  |  |  | 7 | Ability to respond to changes to scope, timeline, and/or resources
| High | Medium High | Medium | Low |  |  | Easy | Moderate | Difficult
|  | x | [5 empty] | x
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Kanban | SCRUM | Waterfall
| 0 | 1 | 0 | 0 |  |  | 0 | 1 | 0
3 | Project team methodology preference/ experience |  |  |  |  | 8 | Level of dependencies within the project
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Many | Some | Few
| x |  | x | x |  |  |  | x
| Waterfall | DMAIC | SCRUM | Kanban |  |  | Waterfall | SCRUM | Kanban
| 1 | 0 | 1 | 1 |  |  | 0 | 1 | 0
4 | Primary project driver |  |  |  |  | 9 | Level of 3rd party vendor management (e.g. RFP)
| Process | Timeline | Unfamiliar | Functionality |  |  | High | Medium | Low or N/A
|  | x | x | x |  |  |  | x
| DMAIC | Waterfall | Kanban | SCRUM |  |  | Waterfall | SCRUM | Kanban
| 0 | 1 | 1 | 1 |  |  | 0 | 1 | 0
5 | Ongoing measures required post project |  |  |  |  | 10 | Delivery approach
| Required | Recommended | Optional | Rarely/ N/A |  |  | Iterative | Constant Flow | Big Bang
|  |  | x | x |  |  | x | x
| DMAIC | Waterfall | SCRUM | Kanban |  |  | SCRUM | Kanban | Waterfall
| 0 | 0 | 1 | 1 |  |  | 1 | 1 | 0
| Planning Methodology | [5 empty] | Execution Methodology
| DMAIC | Waterfall | SCRUM | Kanban |  |  | Waterfall | SCRUM | Kanban
| 1 | 0 | 0 | 1 |  |  | 0 | 0 | 1
| 1 | 0 | 0 | 0 |  |  | 0 | 1 | 0
| 0 | 1 | 1 | 1 |  |  | 0 | 1 | 0
| 0 | 1 | 1 | 1 |  |  | 0 | 1 | 0
| 0 | 0 | 1 | 1 |  |  | 0 | 1 | 1
| 2 | 2 | 3 | 4 |  |  | 0 | 4 | 2
Kan-SCRUM
SCRUM